## Sheet1
[6 empty] | Charlie | Alvin | [10 empty] | Alvin | Craig | [10 empty] | Craig | Wendy | [10 empty] | Wendy
| 2024 |  |  |  |  | 2024 | 2024 | [5 empty] | 2025 |  |  |  |  | 2025 | 2025 | [5 empty] | 2026 |  |  |  |  | 2025 | 2026 | [5 empty] | 2027 |  |  |  |  | 2027 | 2027 | [5 empty] | 2028 |  |  |  |  | 2028
Fundraiser | JAN | FEB | MAR | APR | MAY | JUN | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
Pints for Polio | 2024 JUN: Committee; 2024 JULY: Sponsors'24; 2024 AUG: Plan & Promote; 2024 OCT: Pints4Polio; 2024 NOV: Review; 2025 JUN: Committee; 2025 JULY: Sponsors'25; 2025 AUG: Plan & Promote; 2025 OCT: Pints4Polio; 2025 NOV: Review; 2025 JUN: Committee; 2026 JULY: Sponsors'26; 2026 AUG: Plan & Promote; 2026 OCT: Pints4Polio; 2026 NOV: Review; 2027 JUN: Committee; 2027 JULY: Sponsors'27; 2027 AUG: Plan & Promote; 2027 OCT: Pints4Polio; 2027 NOV: Review; 2028 JUN: Committee
TOAST | 2024 JUN: Committee; 2024 JULY: Sponsors'25; 2024 AUG: Plan & Promote; 2024 NOV: TOAST; 2024 DEC: Review; 2025 JAN: Reserve; 2025 APR: Promote; 2025 JUN: Committee; 2025 JULY: Sponsors'26; 2025 AUG: Plan & Promote; 2025 NOV: TOAST; 2025 DEC: Review; 2026 JAN: Reserve; 2026 APR: Promote; 2025 JUN: Committee; 2026 JULY: Sponsors'27; 2026 AUG: Plan & Promote; 2026 NOV: TOAST; 2026 DEC: Review; 2027 JAN: Reserve; 2027 APR: Promote; 2027 JUN: Committee; 2027 JULY: Sponsors'28; 2027 AUG: Plan & Promote; 2027 NOV: TOAST; 2027 DEC: Review; 2028 JAN: Reserve; 2028 APR: Promote; 2028 JUN: Committee
Cash Raffle | 2024 AUG: Committee; 2024 SEP: Location; 2024 OCT: Planning; 2024 NOV: Sponsors'25; 2024 DEC: Planning; 2025 JAN: Promote; 2025 MAR: Raffle; 2025 APR: Review; 2025 AUG: Committee; 2025 SEP: Location; 2025 OCT: Planning; 2025 NOV: Sponsors'26; 2025 DEC: Planning; 2026 JAN: Promote; 2026 MAR: Raffle; 2026 APR: Review; 2026 AUG: Committee; 2026 SEP: Location; 2026 OCT: Planning; 2026 NOV: Sponsors'27; 2026 DEC: Planning; 2027 JAN: Promote; 2027 MAR: Raffle; 2027 APR: Review; 2027 AUG: Committee; 2027 SEP: Location; 2027 OCT: Planning; 2027 NOV: Sponsors'28; 2027 DEC: Planning; 2028 JAN: Promote; 2028 MAR: Raffle; 2028 APR: Review
Golf Tournament | 2024 AUG: Location; 2024 OCT: Committee; 2024 NOV: Sponsors'25; 2024 DEC: Planning; 2025 FEB: Promote; 2025 MAY: Golf; 2025 JUN: Review; 2025 AUG: Location; 2025 OCT: Committee; 2025 NOV: Sponsors'26; 2025 DEC: Planning; 2026 FEB: Promote; 2026 MAY: Golf; 2025 JUN: Review; 2026 AUG: Location; 2026 OCT: Committee; 2026 NOV: Sponsors'27; 2026 DEC: Planning; 2027 FEB: Promote; 2027 MAY: Golf; 2027 JUN: Review; 2027 AUG: Location; 2027 OCT: Committee; 2027 NOV: Sponsors'28; 2027 DEC: Planning; 2028 FEB: Promote; 2028 MAY: Golf; 2028 JUN: Review
Service
Alzheimer's walk | 2024 AUG: Committee; 2024 SEP: Promote; 2024 NOV: Alz Walk; 2024 DEC: Review; 2025 AUG: Committee; 2025 SEP: Promote; 2025 NOV: Alz Walk; 2025 DEC: Review; 2026 AUG: Committee; 2026 SEP: Promote; 2026 NOV: Alz Walk; 2026 DEC: Review; 2027 AUG: Committee; 2027 SEP: Promote; 2027 NOV: Alz Walk; 2027 DEC: Review
Hand-In-Hand | 2024 JULY: Committee; 2024 AUG: ID Youth; 2024 SEP: Logistics; 2024 DEC: H-in-H; 2025 JAN: Review; 2025 MAR: Recruit & discuss; 2025 MAY: Confirm youth agency; 2025 JULY: Committee; 2025 SEP: Logistics; 2025 DEC: H-in-H; 2026 JAN: Review; 2026 APR: Confirm youth agency; 2026 JULY: Committee; 2026 SEP: Logistics; 2026 DEC: H-in-H; 2027 JAN: Review; 2027 JULY: Committee; 2027 AUG: ID Youth; 2027 SEP: Logistics; 2027 DEC: H-in-H; 2028 JAN: Review
Food Pantry | 2024 DEC: Planning; 2025 JAN: Promote; 2025 FEB: Food Drive; 2025 MAR: Review; 2025 DEC: Planning; 2026 JAN: Promote; 2026 FEB: Food Drive; 2026 MAR: Review; 2026 DEC: Planning; 2027 JAN: Promote; 2027 FEB: Food Drive; 2027 MAR: Review; 2027 DEC: Planning; 2028 JAN: Promote; 2028 FEB: Food Drive; 2028 MAR: Review
Amphitheatre Cleanup | 2025 FEB: Recruit; 2025 MAR: Planning; 2025 APR: Amph C/U; 2025 MAY: Review; 2026 FEB: Recruit; 2026 MAR: Planning; 2026 APR: Amph C/U; 2026 MAY: Review; 2027 FEB: Recruit; 2027 MAR: Planning; 2027 APR: Amph C/U; 2027 MAY: Review; 2028 FEB: Recruit; 2028 MAR: Planning; 2028 APR: Amph C/U; 2028 MAY: Review
Youth Services
4 Way Speech Contest | 2024 OCT: Selection; 2024 NOV: Planning; 2024 DEC: Confirm; 2025 JAN: Promote; 2025 FEB: Speech; 2025 MAR: Review
RYLA | 2025 JAN: Recruit; 2025 FEB: Planning; 2025 MAR: Sponsors; 2025 MAY: Promote; 2025 JUN: RYLA
Student of the Month | 2025 MAY: School; 2025 JUN: SOM dates; 2026 MAY: School; 2025 JUN: SOM dates; 2027 MAY: School; 2027 JUN: SOM dates; 2028 MAY: School; 2028 JUN: SOM dates
Public Image
YMCA Comm Partner Day | 2024 JULY: Reserve; 2024 AUG: Recruit; 2024 SEP: Planning; 2024 NOV: Y Partner; 2024 DEC: Review; 2025 JULY: Reserve; 2025 AUG: Recruit; 2025 SEP: Planning; 2025 NOV: Y Partner; 2025 DEC: Review; 2026 JULY: Reserve; 2026 AUG: Recruit; 2026 SEP: Planning; 2026 OCT: Y Partner; 2026 NOV: Review; 2027 JULY: Reserve; 2027 AUG: Recruit; 2027 SEP: Planning; 2027 OCT: Y Partner; 2027 NOV: Review
Clemmons Comm. Day | 2024 OCT: Reserve; 2025 FEB: Recruit; 2025 MAR: Planning; 2025 APR: CommDay; 2025 MAY: Review; 2025 OCT: Reserve; 2026 FEB: Recruit; 2026 MAR: Planning; 2026 APR: CommDay; 2026 MAY: Review; 2026 OCT: Reserve; 2027 FEB: Recruit; 2027 MAR: Planning; 2027 APR: CommDay; 2027 MAY: Review; 2027 OCT: Reserve; 2028 FEB: Recruit; 2028 MAR: Planning; 2028 APR: CommDay; 2028 MAY: Review
Membership
Discover Rotary | 2024 JULY: Planning; 2024 SEP: Promote; 2024 OCT: Dis.Rotary; 2024 NOV: Review; 2025 JAN: Recruit; 2025 FEB: Planning; 2025 MAR: Promote; 2025 MAY: Dis. Rotary
Social | bar: 2024 JUN
Christmas Party | 2024 SEP: Location; 2024 OCT: Planning; 2024 DEC: Party; 2025 SEP: Location; 2025 OCT: Planning; 2025 DEC: Party; 2026 SEP: Location; 2026 OCT: Planning; 2026 DEC: Party; 2027 SEP: Location; 2027 OCT: Planning; 2027 DEC: Party
Pond Party | 2024 JULY: Review; 2025 JAN: Confirm; 2025 APR: Planning; 2025 JUN: Pond Prty; 2025 JULY: Review; 2026 JAN: Confirm; 2026 APR: Planning; 2025 JUN: Pond Prty; 2026 JULY: Review; 2027 JAN: Confirm; 2027 APR: Planning; 2027 JUN: Pond Prty; 2027 JULY: Review; 2028 JAN: Confirm; 2028 APR: Planning; 2028 JUN: Pond Prty
Awards Banquet | 2024 JULY: Review; 2025 JAN: Location; 2025 FEB: Committee; 2025 MAR: Planning; 2025 JUN: Awards; 2025 JULY: Review; 2026 JAN: Location; 2026 FEB: Committee; 2026 MAR: Planning; 2025 JUN: Awards; 2026 JULY: Review; 2027 JAN: Location; 2027 FEB: Committee; 2027 MAR: Planning; 2027 JUN: Awards; 2027 JULY: Review; 2028 JAN: Location; 2028 FEB: Committee; 2028 MAR: Planning; 2028 JUN: Awards
Pres-Elect
Nominating Committee | 2024 AUG: Committee; 2024 SEP: Planning; 2024 DEC: New Board; 2025 AUG: Committee; 2025 SEP: Planning; 2025 DEC: New Board; 2026 AUG: Committee; 2026 SEP: Planning; 2026 DEC: New Board; 2027 AUG: Committee; 2027 SEP: Planning; 2027 DEC: New Board
Board Retreat | 2025 JAN: Location; 2025 MAR: Planning; 2025 MAY: Brd retreat; 2025 JUN: Review; 2026 JAN: Location; 2026 MAR: Planning; 2026 MAY: Brd retreat; 2025 JUN: Review; 2027 JAN: Location; 2027 MAR: Planning; 2027 MAY: Brd retreat; 2027 JUN: Review; 2028 JAN: Location; 2028 MAR: Planning; 2028 MAY: Brd retreat; 2028 JUN: Review
Match Grant Application | 2025 FEB: Planning; 2025 MAY: DMG due; 2026 FEB: Planning; 2026 MAY: DMG due; 2027 FEB: Planning; 2027 MAY: DMG due; 2028 FEB: Planning; 2028 MAY: DMG due
District Conference | 2025 JAN: Promote; 2025 APR: Event; 2025 MAY: Review; 2026 JAN: Promote; 2026 APR: Event; 2026 MAY: Review; 2027 JAN: Promote; 2027 APR: Event; 2027 MAY: Review